## Team details
Team Name | KICKSTARTS
Team Size | 4
Member1 | P N Naga Sai Akhil Abhiram(22JR1A4252)
Member2 | B Venkata Rupavardhan(22JR1A4338)
Member3 | K Hitesh Krishna (22J
Member4 | G Nakul Sri Sai (22JR1A4355)
Scrum master | AKHIL
Product Owner | Satyaveer Soma
Project Start Date | 2025-12-25
Project End Date | 2026-01-24
Project Title | Gas Ageny Management(GAM)
Number of Sprints | 4
Duration per sprint | 1 week
No of hours spent by each member per sprint | 42 hours
Total number of hours spent by all members | 840 hours
Review by experts

## Working agreement
Duration of sprint | 1 week
Time of daily scrum | 45mins
Place of daily scrum | R AND D BLOCK LAB

## Definition of done
Every item of pb should satisfy the below dod
S.No. | CheckList
1 | All acceptance criteria should pass
2 | no open defects
3 | fundamental documentation should be done (either late or continuous)
4 | Integration testing should be done
5 | Code review must be done and feedback must be implemented

## Backlog Sheet
Order/Priority | Backlog item description | Remarks | Dependency of backlog item on another
1 | Read the entire use case and prepared a high level design which includes Application structure, Cases, Data Model, Organization Structure (including Actors, Access Groups, Sample Operators) | Completed | No Dependency
2 | Application Creation | Completed | 1
Create Gas Management Agency as Application Name
Create organization , division and unit records
Create Access groups
Create a Dynmaic Operator
Create Operator
3 | Creating Case lifecycle | Completed | 1
Create Connection Transfer and Booking Compliants Case Lifecycle
Create Gas Booking as Main Case Lifecycle
4 | Create Data types | Completed | 1
Create data types such as Compliants , Connection Transfer , Consumer , Distributers Dataset , Feedback , Payment Details.------
5 | Design UI forms and Validations
| Design UI forms for Consumer Registration and Login | Completed | 3,4
| Design UI form for selecting Cylinder Type and Gas Booking | Completed | 3,4
| Design UI form for Payment and Cylinder Count | Completed | 3,4
| Design UI form for FeedBack | Completed | 3,4
| Design UI form for Connection Transfer Type | Completed | 3,4
| Design UI form for Same City Transfer and Different City Transfer | Completed | 3,4
| Design UI form for Manager Approval and their Rejection Paths | Completed | 3,4
| Design UI form for Selecting a Compliants | Completed | 3,4
| Design UI form for Compliant Review and Solution | Completed | 3,4
6 | Process Design | Completed | 3,4
6.1 | Gas Booking
i. Consumer logs into the application using username and password ii. System displays consumer details along with number of subsidized cylinders available. iii. Consumer selects the type of cylinder (Domestic / Commercial). iv. Based on the number of cylinders consumed, subsidy rule is applied automatically. v. System calculates the amount based on subsidy eligibility. vi. Consumer submits the booking request. vii. Booking request is sent to distributor for processing. viii. Booking confirmation mail is sent to the consumer.
6.2 | Connection Transfer
| 1.Same City Transfer | Completed | 3,4
i. Consumer logs into the application. ii. Consumer selects connection transfer option. iii. Consumer enters new address details within the same city. iv. Consumer submits Subscription Voucher details. v. Manager verifies the transfer request. vi. On approval, address is updated and confirmation mail is sent to consumer
| 2.Different City Transfer | Completed | 3,3
i. Consumer initiates transfer request for a different city. ii. Consumer surrenders gas equipment to existing distributor. iii. System generates Termination Voucher (TV). iv. Deposit amount is refunded to consumer. v. Consumer selects new distributor in the new city. vi. Manager verifies and approves the request. vii. Confirmation mail is sent to consumer.
6.3 | Booking Compliants
| i. Consumer logs into the application. ii. Consumer raises a complaint related to booking or delivery. iii. Complaint details are captured in the system. iv. Complaint request is sent to manager for review. v. Manager approves or rejects the complaint. vi. SLA and wait condition is applied for resolution. vii. Solution or rejection mail is sent to the consumer. | Completed | 3,4
7 | Reports Design : Design consumer report to display number of cylinders booked and amount paid for a given period | Completed | 2
8 | Field Validations | Completed | 5
9 | Portals Creation | Completed | 3
| Consumer Portal | Completed | 3
| Manager Portal | Completed | 3
10 | Customizing login screens, application skin design | Completed | 2
11 | End to End Testing

## Sprint Planning
Any additional data that team wants to record during planning
Sprint planning conducted based on prioritized product backlog items.
Scope of sprint finalized considering academic timeline and complexity of Pega case types.
Each backlog item mapped to corresponding Pega case lifecycle stages.
Dependencies between consumer registration, booking, payment and transfer flows identified.
SLA requirements discussed for booking confirmation and complaint resolution.
Email notifications planned for registration, booking confirmation, transfer and complaints.
Team agreed to follow Pega guardrails and minimize warnings during implementation
Risk identified: dependency on approval flows and external email configuration
Testing strategy discussed for each sprint before moving to next sprint.

## Sprint1
Backlog Item 1 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Read the entire use case and prepare a high level design | Creating High Level Design which includes Application structure, Cases, Data Model, Organization Structure (including Actors,Operators and Access Groups) |  | Completed | Requirements Discussion | Understanding all the requirments and mind sharing | 2 | 2 | 0 | Completed | All
|  |  |  | Organization Structure | Identify Organization divisions, units | 2 | 2 | 0 | Completed | All
|  |  |  | Case Type Identification | Identify required case types (Gas Booking, Connection Transfer, Complaints, Feedback) | 2 | 2 | 0 | Completed | All
|  |  |  | Data Model | Identify all the required data types and draw the data model design | 4 | 4 | 0 | Completed | All
Backlog item 2
Name | Description | Size | Status | Tasks
Application Design | Application Creation |  | Completed | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
|  |  |  | Application Creation | Creating GasMS application, organization record and access groups | 2 | 2 | 0 | Completed | All
Backlog item 3
Name | Description | Size | Status | Tasks
Case Design | Creating Case Types |  | Completed | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
|  |  |  | Case Design | Case life cycle for Gas Booking, Connection Transfer and Complaints | 4 | 4 | 0 | Completed | All
Backlog Item 4
Name | Description | Size | Status | Tasks
Data Design | Creating all the data types |  | Completed | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
|  |  |  | Data Design | Creating data types like Consumer, Distributor, Payment Details, Feedback and local data storgae | 2 | 2 | 0 | Completed | All

## Sprint2
Backlog item 5.1 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Consumer Login | Create UI screens with required validations and submission actions for Consumer Login |  | Completed | Create Login UI | Design login screen for consumer login | 30 min | 30 min | 0 | Completed | All
|  |  |  | Apply Validations | Apply validations for Username and passwords | 1 | 1 | 0 | Completed | All
Backlog item 5.2 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Consumer Registration | Create UI screens for consumer registration with validations |  | Completed | Create Registration UI | Design registration form for new consumer | 30 min | 30 min | 0 | Completed | All
|  |  |  | OTP Email Configuration | Configure OTP email for registration | 1 hour | 1 hour | 0 | Completed | All
|  |  |  | Apply Field Validations | Apply mandatory and format validations | 20 minutes | 20 minutes | 0 | Completed | All
|  |  |  | Review and Submit Actions | Review UI and submit registration | 20 minutes | 20 minutes | 0 | Completed | All
Backlog item 5.3 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Feedback | Create UI screens for consumer feedback |  | Completed | Feedback Form UI | Design feedback form (Good / Average / Poor) and other fleids | 30 min | 30 min | 0 | Completed | All
|  |  |  | Feedback Email | Configure feedback notification email | 30 min | 30 min | 0 | Completed | All
Backlog item 5.4 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Payment | Create UI screens for payment and approval |  | Completed | Payment Mode Selection | Create UI for online and offline payment and type of payment | 1 hour | 1 hour 30 minutes | -30 minutes | Completed | All
|  |  |  | Payment Validation | Apply validation for payment details | 15 min | 15 min | 0 | Completed | All
|  |  |  | Payment Approval UI | Configure approval screen for Manager | 15 min | 15 min | 0
Backlog item 5.5 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Gas Booking | Create UI screens for gas booking process |  | Completed | Consumer Details Display | Display consumer details after login | 30 min | 30 min | 0 | Completed | All
|  |  |  | Cylinder Type Selection | Create UI for domestic and commercial selection | 30 min | 30 min | 0 | Completed | All
|  |  |  | Apply Subsidy Logic | Implement subsidy validation logic | 1 hour 30 Min | 2 hours | -30 mins | Completed | All
|  |  |  | Review and Submit Booking | Review booking details and submit | 15 min | 15 min | 0 | Completed | All
Backlog item 5.6 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Connection Transfer | Create UI screens to initiate gas connection transfer request |  | Completed | Connection Transfer UI | Create UI for initiating connection transfer | 30 min | 30 min | 0 | Completed | All
|  |  |  | Transfer Type Selection | Allow selection of Same City / Different City and passes to that stages | 30 min | 30 min | 0 | Completed | All
|  |  |  | Apply Validations | Applied basic validations on the required proprties. | 15 min | 15 min | 0 | Completed | All
Backlog item 5.7 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Same City and Different City Transfer | Create UI screens for same city and different city transfer flows |  | Completed | Same City Transfer UI | Create UI to enter new address and submit SV | 1 hour | 1 hour | 0 | Completed | All
|  |  |  | Different City Transfer UI | Create UI for equipment surrender and TV generation | 1 hour | 1 hour 30 min | -30 mins | Completed | All
|  |  |  | Manager Verification UI | Configure verification screen for Manager | 30 min | 30 min | 0 | Completed | All
|  |  |  | Confirmation Emails | Configure confirmation email after transfer | 15 min | 15 min | 0 | Completed | All
Backlog item 5.8 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Create UI for Booking Complaints | Create UI screens for booking and delivery complaints |  | Completed | Complaint Registration UI | Create UI to raise booking complaint | 30 min | 30 min | 0 | Completed | All
|  |  |  | Complaint Review UI | Configure manager review and approval screen | 15 min | 15 min | 0 | Completed | All
|  |  |  | SLA & Wait Configuration | Configure SLA and wait step for complaints | 15 min | 15 min | 0 | Completed | All
|  |  |  | Complaint Email Correspondence | Configure solution and rejection emails | 15 min | 15 min | 0 | Completed | All

## Sprint3
Backlog item 6.1 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Connection Transfer | i. Report Defintion ii. Data Transform iii.Section |  | Completed | Created Properties and DataType | Creating | 30 min | 30 min | 0 | Completed | B Rupavardhan , K Hitesh
|  |  |  | Created Sections | Created a pdf "Termination Vochor" for different city conncection transfer and a pdf any of the | 3 hrs | 3 hrs | 0 | Completed | B Rupavardhan , K Hitesh
|  |  |  | Created a | Created a | 1 hrs | 1 hrs | 0 | Completed | P N Naga Sai Akhil Abhiram
Backlog item 6.2 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Payment | i.Data transform |  | Completed | Payment | Created a Data Transform for calculating total amount based on the cylinder type , if he is new consumer then added the intial depoit to the total amout | 1 hrs | 1 hrs | 0 | Completed | K.Hitesh Krishna, G Nakul Sri Sai
Backlog item 6.3 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Gas Booking | i. Report Defintion ii. Data Transform iii.Data Page iv. Section |  | Completed | Created property | Added a property "subsidied cylinders remaing " and initiasied it with a value count of 12 | 30 min | 30 min | 0 | Completed | P N Naga Sai Akhil Abhiram ,G Nakul Sri Sai
|  |  |  | Created a Section | Created a pdf for subcrictiion vochur for the new consumer | 1 hrs | 1 hrs | o | Completed | P N Naga Sai Akhil Abhiram ,G Nakul Sri Sai
|  |  |  | Created data page | i.Created a data page for updating the subsised cylider count each time the consumer book a cylinder upto 12 subsised cylinder | 2 hrs | 2 hrs | 0 | Completed | P N Naga Sai Akhil Abhiram ,G Nakul Sri Sai
Backlog item 6.4 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Updation | i.Data Page |  | Completed | Created Property | Created a property for entering the new address in same city stage | 30 min | 30 min | 0 | Completed | All
|  |  |  | Created Data Page | Created Updation for address when the customer selected connection transfer type as same city | 2hrs | 2 hours | 0 | Completed | All
Backlog item 6.5 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Savable | i.Data Page |  | Completed | Created Property | Created properties for saving registration , gas booking , Payment , Compliants , Connection transfer | 30 min | 30 min | 0 | Completed | All
|  |  |  | Created Data Page | Created Savable data pages for new consumer registration , gas booking , Payment , Compliants , Connection transfer | 3hrs | 3 hours | 0 | Completed | All

## Sprint 4
Backlog item 7 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Reports | Report on Gas Booking |  | Completed and updated in drive | Reports | Report on Desk Reservati | 2 hrs | 2 hrs | 0 | Completed | K Hemanth Krishna
|  |  |  | Reports | Report on Desk Reservation on Daily Basics | 2 hrs | 2 hrs | 0 | Completed | K Hemanth Krishna
|  |  |  | Reports | Report on Desk Reservation on Daily Basics | 2 hrs | 2 hrs | 0 | Completed | K Hemanth Krishna
Backlog item 9 |  |  |  | Tasks
Name | Description | Size | Status | Name | Description | Planned Effort(hrs) | Spent Effort(Hrs) | Remaining effort(hrs) | Status | Member working on task
Portals | Portals Creation |  | Completed and updated in drive | Cunsumer Portal Creation | Created Consumer Portal using App Studio | 10 min | 10 min | 0 | Completed | ALL
|  |  |  | Navigation Setup | Configured navigation menu for Consumer Portal | 20 min | 20 min | 0 | Completed | ALL
|  |  |  | Manager Portal Creation | Created Manager Portal | 10 min | 10 min | 0 | Completed | ALL
|  |  |  | Approval Sections | Created approval sections for booking, transfer and complaints | 10 min | 10 min | 0 | Completed | ALL
|  |  |  | Dashboard Configuration | Configured dashboard for pending approvals | 1 hrs | 1 hrs | 0 | Completed | ALL

## Sprint Review
Sprint Number | Review Comments | To be added to backlog or not
Sprint 1 | High level design and application structure were clearly defined and reviewed successfully | No
Sprint 1 | Case types identified correctly and aligned with the use case | No
Sprint 1 | Data model needs minor refinement for future extensibility | Yes
Sprint 1 | Access group and role definitions were reviewed and approved | No
Sprint 1 | Naming conventions for data elements could be improved | Yes
Sprint 1 | Initial UI screens meet basic functional expectations | No
Sprint 2 | Consumer registration and login flow works as expected | No
Sprint 2 | Gas booking flow including subsidy logic reviewed and validated | No
Sprint 2 | Payment calculation logic works correctly for all test cases | No
Sprint 2 | UI validations can be enhanced for better user experience | Yes
Sprint 2 | Email notifications are triggered correctly for booking and payment | No
Sprint 2 | Error messages need to be more user friendly | Yes
Sprint 2 | Connection transfer flow logic was reviewed and approved | No
Sprint 2 | Additional confirmation message suggested before final submission | Yes
Sprint 3 | Complaint management flow reviewed and meets business requirements | No
Sprint 3 | SLA configuration is correct but needs additional monitoring | Yes
Sprint 3 | Report data accuracy validated for sample records | No
Sprint 3 | Report filters could be enhanced for better usability | Yes
Sprint 3 | Data pages perform efficiently under test conditions | No
Sprint 4 | Consumer portal navigation reviewed and accepted | No
Sprint 4 | Distributor portal dashboards display correct pending tasks | No
Sprint 4 | Portal access control reviewed for different user roles | No
Sprint 4 | UI consistency across portals is satisfactory | No
Sprint 4 | Final end-to-end flow demonstrated successfully | No
Sprint 4 | Performance optimization for reports suggested | Yes
Sprint 4 | Overall system meets academic project expectations | No
Sprint 4 | Minor UI enhancements suggested for better presentation | Yes
Sprint 4 | Final demo feedback incorporated successfully | No

## Daily Scrum
Impediment ID | Description | Backlog item | Status
IMP-01 | Initial understanding of Gas Agency business workflow and domain terminology required additional time | Sprint 1 – High Level Design | Resolved
IMP-02 | Delay in identifying correct case types and stages for GasMS | Sprint 1 – Case Design | Resolved
IMP-03 | Clarification needed on consumer registration fields and validation rules | Sprint 1 – Consumer Registration | Resolved
IMP-04 | Difficulty in designing data model for consumer, distributor and payment details | Sprint 1 – Data Design | Resolved
IMP-05 | Implementation of declare expression for subsidy and amount calculation took extra effort | Sprint 2 – Payment | Resolved
IMP-06 | Understanding subsidy rule (maximum 12 cylinders per year) required multiple test scenarios | Sprint 2 – Gas Booking | Resolved
IMP-07 | Differentiating same city and different city connection transfer flows required clarification | Sprint 2 – Connection Transfer | Resolved
IMP-08 | Data page configuration for fetching dynamic booking and consumer details needed refinement | Sprint 3 – Data Pages | Resolved
IMP-09 | Portal access control required proper mapping of access groups and roles | Sprint 4 – Portals | Resolved
IMP-10 | Dashboard display for distributor approvals needed UI adjustments | Sprint 4 – Distributor Portal | Resolved

## Retro
Sprint Number | Actionable improvement | Prioritized for implementation(Yes/No)
Sprint 1 | Spend more time upfront understanding the Gas Agency domain and terminology to reduce rework during case design | Yes
Sprint 1 | Finalize data model early to avoid changes in later sprints | Yes
Sprint 1 | Define naming conventions for case types, stages and data elements | Yes
Sprint 1 | Improve coordination while identifying access groups and roles | No
Sprint 1 | Maintain a checklist for mandatory Pega configurations during application creation | Yes
Sprint 2 | Break UI-related tasks into smaller tasks for better tracking | Yes
Sprint 2 | Validate business rules like subsidy logic with multiple test scenarios earlier | Yes
Sprint 2 | Improve time estimation for declare expressions and validations | No
Sprint 2 | Configure email notifications earlier to avoid last-minute delays | Yes
Sprint 2 | Perform peer review of booking and payment flows before sprint closure | Yes
Sprint 3 | Create reusable data pages instead of multiple similar ones | Yes
Sprint 3 | Reduce dependency on manual testing by using test cases in Pega | No
Sprint 3 | Allocate buffer time for SLA configuration and tuning | Yes
Sprint 3 | Standardize error messages across all case types | No
Sprint 3 | Improve visibility of rule dependencies between data pages and reports | Yes
Sprint 4 | Design portals with navigation structure finalized before implementation | Yes
Sprint 4 | Improve dashboard usability for distributor approvals | Yes
Sprint 4 | Add filters and sorting options to reports for better usability | Yes
Sprint 4 | Perform UI consistency checks across consumer and distributor portals | Yes
Sprint 4 | Improve sprint review preparation with clear demo flow | Yes
Sprint 4 | Maintain a final checklist to ensure all backlog items are completed | Yes
Sprint 4 | Track technical debt items separately for future improvements | No
Sprint 4 | Improve time management during final sprint to avoid last-day rush | Yes
Sprint 4 | Ensure all guardrail warnings are reviewed and minimized | Yes